## Sheet1
| Requirement | Details | Total Estimate in Hrs | Estimate in Hrs | Status | ETA | Completion Date | Comments
1 | MOD Migration to MyAdvisor |  | 56 |  |  |  |  | Script is ready to be applied to production. Awaiting on Ken to provide go ahead. 10/24: Moved to production and received feedback from business that it's working
1.1 |  | Pull MOD data to MyAdvisor |  |  | Completed |  | 2023-10-17
1.1.1 |  | Insert MOD excel data to SQL table |  | 16 | Completed |  | 2023-10-17
1.1.2 |  | Insert MOD & CBM mapping to SQL table |  | 16 | Completed |  | 2023-10-17
1.1.3 |  | Write SQL to create entries in PFTWO table |  | 24 | Completed |  | 2023-10-17
|  | Complete load of MOD data |  |  | Awaiting on business
2 | WAM Asset History Modifications |  | 60 |  | In progress | 2023-12-15
2.1 |  | Pull in Run based Meter Reading data from Oneview |  | 24
2.2 |  | Change WAM Asset History grid to include run data *operhrs |  | 20
2.3 |  | Update user interface to open OneView Job page |  | 16
3 | Modify Oneview Asset feed |  | 36 |  | In progress | 2023-11-17
3.1 |  | Ensure no impact to OneView offline client
3.2 |  | Pull Fixed Asset data in Oneview |  | 16
3.3 |  | Create SQL job to fetch data |  | 4
3.4 |  | Setup DV & QA environment for testing |  | 16
4 | Display MIP information in OneView Job Asset tab |  | 32 |  |  | 2023-12-01
4.1 |  | Fetch & Save MIP calculation from MyAdvisor |  | 16
4.2 |  | Display MIP calculation in OneView |  | 16
5 | Testing |  |  | 20 |  | 2023-12-15
6 | Deployment |  |  | 20 |  | 2023-12-22
| Total |  |  | 224
Note
MOD information from TOPS will be provided in Excel. No need to get data from TOPS using script
There will be no changes made on OneView offline app or in reports. All changes will be made on OneView Website.